## Robin_&_Legatum - Master
S.No |  | Table Type | Table Name | Stored procedure Name | SQL Script Name | SIT Data Comparison / Remove Temp. Adj | Comments | MYMI-Test
1 | Inward Data Comparison MYMI & DAL | DIM | DIM.INW_GroupClass | RITC_EXT.INW_Dim_GroupClass | Check_DataComparison_DIM_INW_Group_Class_v0.3.SQL | Passed |  | Passed
2 |  |  | DIM.INW_Loss | RITC_EXT.INW_Dim_Loss | Check_DataComparison_DIM_INW_Loss_v0.1.SQL | Passed |  | Passed
3 |  |  | DIM.INW_LossEvent | RITC_EXT.INW_Dim_LossEvent | Check_DataComparison_DIM_INW_LossEvent_v0.1.SQL | Passed |  | Passed
4 |  |  | DIM.INW_RISK | RITC_EXT.INW_Dim_Risk | Check_DataComparison_DIM_INW_RISK_v0.1.SQL | Passed | Failed due to Performance Issue. Performance issue fixed | Passed
5 |  | FACT | FACT.INW_OSClaim | RITC_EXT.INW_Fact_OSClaim | Check_DataComparison_FACT_INW_OSClaim_v0.2.SQL | Passed |  | Failed
6 |  |  | FACT.INW_PaidClaim | RITC_EXT.INW_Fact_PaidClaim | Check_DataComparison_FACT_INW_PaidClaim_v0.2.SQL | Passed |  | Passed
7 |  |  | FACT.INW_Premium | RITC_EXT.INW_Fact_Premium | Check_DataComparison_FACT_INW_Premium_v0.2.SQL | Passed |  | Passed
8 |  |  | FACT.INW_WrittenPremium | RITC_EXT.INW_Fact_WrittenPremium | Check_DataComparison_FACT_INW_WrittenPremium_v0.2.SQL | Passed |  | Passed
9 |  | Control | Control.INW_OSClaim | RITC_EXT.INW_Control_OSClaim | Check_DataComparison_Control_INW_OSClaim_v0.1.SQL | Passed | Bug #93767 raised.Defect fixed and it's working - 24/06/2022 | Failed
10 |  |  | Control.INW_PaidClaim | RITC_EXT.INW_Control_PaidClaim | Check_DataComparison_Control_INW_PaidClaim_v0.1.SQL | Passed | Bug #93767 raised.Defect fixed and it's working - 24/06/2022 | Passed
11 |  |  | Control.INW_Premium | RITC_EXT.INW_Control_Premium | Check_DataComparison_Control_INW_Premium_v0.1.SQL | Passed |  | Passed
12 |  |  | Control.INW_WrittenPremium | RITC_EXT.INW_Control_WrittenPremium | Check_DataComparison_Control_INW_WrittenPremium_v0.1.SQL | Passed |  | Passed
13 | 84071 Removal of Temp Adjustment from INWARD FACT | FACT | FACT.INW_OSClaim | RITC_EXT.INW_Fact_OSClaim | 84071_Check_Temp_Adj_Data_INW_FACT_OSClaim_v0.1.SQL | Passed
14 |  |  | FACT.INW_PaidClaim | RITC_EXT.INW_Fact_PaidClaim | 84071_Check_Temp_Adj_Data_INW_FACT_PaidClaim_v0.1.SQL | Passed
15 |  |  | FACT.INW_Premium | RITC_EXT.INW_Fact_Premium | 84071_Check_Temp_Adj_Data_INW_FACT_Premium_v0.1.SQL | Passed
16 |  |  | FACT.INW_WrittenPremium | RITC_EXT.INW_Fact_WrittenPremium | 84071_Check_Temp_Adj_Data_INW_FACT_WrittenPremium_v0.1.SQL | Passed
17 |  | Control | Control.INW_OSClaim | RITC_EXT.INW_Control_OSClaim | 84071_Check_Temp_Adj_Data_INW_Control_OSClaim_v0.1.SQL | Passed
19 |  |  | Control.INW_PaidClaim | RITC_EXT.INW_Control_PaidClaim | 84071_Check_Temp_Adj_Data_INW_Control_PaidClaim_v0.1.SQL | Passed
20 |  |  | Control.INW_Premium | RITC_EXT.INW_Control_Premium | 84071_Check_Temp_Adj_Data_INW_Control_Premium_v0.1.SQL | Passed
21 |  |  | Control.INW_WrittenPremium | RITC_EXT.INW_Control_WrittenPremium | 84071_Check_Temp_Adj_Data_INW_Control_WrittenPremium_v0.1.SQL | Passed
22 | Outward | DIM | DIM.OUTW_GroupClass |  | Check_DataComparison_C_DIM_OUTW_Group_Class_v0.2.SQL | Passed |  | Passed
23 |  |  | DIM.OUTW_LossEvent |  | Check_DataComparison_C_DIM_OUTW_LossEvent_v0.2.SQL | Passed |  | Passed
24 |  |  | DIM.OUTW_RIContract |  | Check_DataComparison_C_DIM_OUTW_RIContract_v0.2.SQL | Passed |  | Passed
25 |  |  | DIM.OUTW_RIContractAcc |  | Check_DataComparison_C_DIM_OUTW_RIContractAcc_v0.2.SQL | Passed |  | Passed
26 |  |  | DIM.OUTW_RIContractCcyLimit |  | Check_DataComparison_C_DIM_OUTW_RIContractCcyLimit_v0.2.SQL | Passed | DataType Issue sorted by inserting the data manually with CAST | Passed
27 |  |  | DIM.OUTW_RIContractIns |  | Check_DataComparison_C_DIM_OUTW_RIContractIns_v0.2.SQL | Passed |  | Passed
28 |  |  | DIM.OUTW_Risk |  | Check_DataComparison_C_DIM_OUTW_Risk_v0.2.SQL | Passed | Column Order issue. CONTRACT_ | Passed
29 |  | FACT | FACT.OUTW_OSClaim |  | Check_DataComparison_C_FACT_OUTW_OSClaim_v0.2.SQL | Passed |  | Passed
30 |  |  | FACT.OUTW_OSPremium |  | Check_DataComparison_C_FACT_OUTW_OSPremium_v0.2.SQL | Passed |  | Passed
31 |  |  | FACT.OUTW_PaidClaim |  | Check_DataComparison_C_FACT_OUTW_PaidClaim_v0.2.SQL | Passed |  | Passed
32 |  |  | FACT.OUTW_PaidPremium |  | Check_DataComparison_C_FACT_OUTW_PaidPremium_v0.2.SQL | Passed |  | Passed
33 |  | Control | Control.OUTW_OSClaim |  | Check_DataComparison_Control_OUTW_OSClaim_v0.1.SQL | Passed |  | Passed
34 |  |  | Control.OUTW_PaidClaim |  | Check_DataComparison_Control_OUTW_PaidClaim_v0.1.SQL | Passed |  | Passed
35 |  |  | Control.OUTW_OSPremium |  | Check_DataComparison_Control_OUTW_OSPremium_v0.1.SQL | Passed |  | Passed
36 |  |  | Control.OUTW_PaidPremium |  | Check_DataComparison_Control_OUTW_PaidPremium_v0.1.SQL | Passed |  | Passed

## BNB Analysis - Prod
ServerName | TableName | ConfigCheck | ExternalSyndicate | BureauNonBureauSwitch | GroupClass | Min_YOA | Max_YOA | IsAdjusted | DimPolicyID | TestResult
MyMI-test | DWH_MI.LatestFactSignedTransaction | Legatum/Robin - ConfigCheck | 1202 | RITC Legatum | DISC 1202 | 2001 | 2002 | 0 | 9531330 | Failed - or N/A for Legatum/Robin | These are the records failure from BNB flag testing in MYMI-Test 7 policies from MYMI tables and same 7 policies from Eclipse_MI tables
MyMI-test | DWH_MI.LatestFactSignedTransactionUnadjusted | Legatum/Robin - ConfigCheck | 1202 | RITC Legatum | DISC 1202 | 2001 | 2002 | 0 | 9531330 | Failed - or N/A for Legatum/Robin
MyMI-test | Eclipse_MI.LatestFactSignedTransaction | Legatum/Robin - ConfigCheck | 1202 | RITC Legatum | DISC 1202 | 2001 | 2002 | 0 | 9531330 | Failed - or N/A for Legatum/Robin
MyMI-test | Eclipse_MI.LatestFactSignedTransactionUnadjusted | Legatum/Robin - ConfigCheck | 1202 | RITC Legatum | DISC 1202 | 2001 | 2002 | 0 | 9531330 | Failed - or N/A for Legatum/Robin
MyMI-test | DWH_MI.LatestFactSignedTransaction | Legatum/Robin - ConfigCheck | 250 | RITC Legatum | DISC 250 | 2000 | 9999 | 0 | 9532632 | Failed - or N/A for Legatum/Robin
MyMI-test | DWH_MI.LatestFactSignedTransactionUnadjusted | Legatum/Robin - ConfigCheck | 250 | RITC Legatum | DISC 250 | 2000 | 9999 | 0 | 9532632 | Failed - or N/A for Legatum/Robin
MyMI-test | Eclipse_MI.LatestFactSignedTransaction | Legatum/Robin - ConfigCheck | 250 | RITC Legatum | DISC 250 | 2000 | 9999 | 0 | 9532632 | Failed - or N/A for Legatum/Robin
MyMI-test | Eclipse_MI.LatestFactSignedTransactionUnadjusted | Legatum/Robin - ConfigCheck | 250 | RITC Legatum | DISC 250 | 2000 | 9999 | 0 | 9532632 | Failed - or N/A for Legatum/Robin
MyMI-test | DWH_MI.LatestFactSignedTransaction | Legatum/Robin - ConfigCheck | 250 | RITC Legatum | DISC 250 | 1993 | 2005 | 0 | 9576184 | Failed - or N/A for Legatum/Robin
MyMI-test | DWH_MI.LatestFactSignedTransactionUnadjusted | Legatum/Robin - ConfigCheck | 250 | RITC Legatum | DISC 250 | 1993 | 2005 | 0 | 9576184 | Failed - or N/A for Legatum/Robin
MyMI-test | Eclipse_MI.LatestFactSignedTransaction | Legatum/Robin - ConfigCheck | 250 | RITC Legatum | DISC 250 | 1993 | 2005 | 0 | 9576184 | Failed - or N/A for Legatum/Robin
MyMI-test | Eclipse_MI.LatestFactSignedTransactionUnadjusted | Legatum/Robin - ConfigCheck | 250 | RITC Legatum | DISC 250 | 1993 | 2005 | 0 | 9576184 | Failed - or N/A for Legatum/Robin
MyMI-test | DWH_MI.LatestFactSignedTransaction | Legatum/Robin - ConfigCheck | 1202 | RITC Legatum | DISC 1202 | 2001 | 9999 | 0 | 9680238 | Failed - or N/A for Legatum/Robin
MyMI-test | DWH_MI.LatestFactSignedTransactionUnadjusted | Legatum/Robin - ConfigCheck | 1202 | RITC Legatum | DISC 1202 | 2001 | 9999 | 0 | 9680238 | Failed - or N/A for Legatum/Robin
MyMI-test | Eclipse_MI.LatestFactSignedTransaction | Legatum/Robin - ConfigCheck | 1202 | RITC Legatum | DISC 1202 | 2001 | 9999 | 0 | 9680238 | Failed - or N/A for Legatum/Robin
MyMI-test | Eclipse_MI.LatestFactSignedTransactionUnadjusted | Legatum/Robin - ConfigCheck | 1202 | RITC Legatum | DISC 1202 | 2001 | 9999 | 0 | 9680238 | Failed - or N/A for Legatum/Robin
MyMI-test | DWH_MI.LatestFactSignedTransaction | Legatum/Robin - ConfigCheck | 2987 | RITC Legatum | DISC UK | 2001 | 2003 | 0 | 9680240 | Failed - or N/A for Legatum/Robin
MyMI-test | DWH_MI.LatestFactSignedTransactionUnadjusted | Legatum/Robin - ConfigCheck | 2987 | RITC Legatum | DISC UK | 2001 | 2003 | 0 | 9680240 | Failed - or N/A for Legatum/Robin
MyMI-test | Eclipse_MI.LatestFactSignedTransaction | Legatum/Robin - ConfigCheck | 2987 | RITC Legatum | DISC UK | 2001 | 2003 | 0 | 9680240 | Failed - or N/A for Legatum/Robin
MyMI-test | Eclipse_MI.LatestFactSignedTransactionUnadjusted | Legatum/Robin - ConfigCheck | 2987 | RITC Legatum | DISC UK | 2001 | 2003 | 0 | 9680240 | Failed - or N/A for Legatum/Robin
MyMI-test | DWH_MI.LatestFactSignedTransaction | Legatum/Robin - ConfigCheck | 2987 | RITC Legatum | PL UK | 2008 | 9999 | 0 | 9782097 | Failed - or N/A for Legatum/Robin
MyMI-test | DWH_MI.LatestFactSignedTransactionUnadjusted | Legatum/Robin - ConfigCheck | 2987 | RITC Legatum | PL UK | 2008 | 9999 | 0 | 9782097 | Failed - or N/A for Legatum/Robin
MyMI-test | Eclipse_MI.LatestFactSignedTransaction | Legatum/Robin - ConfigCheck | 2987 | RITC Legatum | PL UK | 2008 | 9999 | 0 | 9782097 | Failed - or N/A for Legatum/Robin
MyMI-test | Eclipse_MI.LatestFactSignedTransactionUnadjusted | Legatum/Robin - ConfigCheck | 2987 | RITC Legatum | PL UK | 2008 | 9999 | 0 | 9782097 | Failed - or N/A for Legatum/Robin
MyMI-test | DWH_MI.LatestFactSignedTransaction | Legatum/Robin - ConfigCheck | 2987 | RITC Legatum | PL UK | 2014 | 9999 | 0 | 9880683 | Failed - or N/A for Legatum/Robin
MyMI-test | DWH_MI.LatestFactSignedTransactionUnadjusted | Legatum/Robin - ConfigCheck | 2987 | RITC Legatum | PL UK | 2014 | 9999 | 0 | 9880683 | Failed - or N/A for Legatum/Robin
MyMI-test | Eclipse_MI.LatestFactSignedTransaction | Legatum/Robin - ConfigCheck | 2987 | RITC Legatum | PL UK | 2014 | 9999 | 0 | 9880683 | Failed - or N/A for Legatum/Robin
MyMI-test | Eclipse_MI.LatestFactSignedTransactionUnadjusted | Legatum/Robin - ConfigCheck | 2987 | RITC Legatum | PL UK | 2014 | 9999 | 0 | 9880683 | Failed - or N/A for Legatum/Robin
ServerName | TableName | ExternalSyndicate | BureauNonBureauSwitch | GroupClass | Min_YOA | Max_YOA | IsAdjusted | DimPolicyID | ExpedtedResult | TestResult
MyMI-prod | DWH.FactSignedTransactionDataHistory | 1202 | Legatum | DISC 1202 | 2001 | 2002 | 0 | 9531330 | Retained | Failed
MyMI-prod | DWH.FactSignedTransactionDataHistory | 1202 | Legatum | DISC 1202 | 2001 | 2001 | 0 | 9680238 | RITC Legatum | Passed
MyMI-prod | DWH.FactSignedTransactionDataHistory | 250 | Legatum | DISC 250 | 2000 | 2000 | 0 | 9532632 | RITC Legatum | Passed
MyMI-prod | DWH.FactSignedTransactionDataHistory | 250 | Legatum | DISC 250 | 1993 | 2005 | 0 | 9576184 | Retained | Failed
MyMI-prod | DWH.FactSignedTransactionDataHistory | 2987 | Legatum | DISC UK | 2001 | 2003 | 0 | 9680240 | Retained | Failed
MyMI-prod | DWH.FactSignedTransactionDataHistory | 2987 | Legatum | PL UK | 2008 | 2008 | 0 | 9782097 | RITC Legatum | Passed
MyMI-prod | DWH.FactSignedTransactionDataHistory | 2987 | Legatum | PL UK | 2014 | 2014 | 0 | 9880683 | RITC Legatum | Passed
ServerName | TableName | ExternalSyndicate | BureauNonBureauSwitch | GroupClass | Min_YOA | Max_YOA | IsAdjusted | DimPolicyID | ExpedtedResult | TestResult
MyMI-prod | Eclipse_MI.FactSignedTransaction | 1202 | Legatum | DISC 1202 | 2001 | 2002 | 0 | 9531330 | Retained | Failed
MyMI-prod | Eclipse_MI.FactSignedTransaction | 1202 | Legatum | DISC 1202 | 2001 | 9999 | 0 | 9680238 | Retained | Failed
MyMI-prod | Eclipse_MI.FactSignedTransaction | 250 | Legatum | DISC 250 | 2000 | 9999 | 0 | 9532632 | Retained | Failed
MyMI-prod | Eclipse_MI.FactSignedTransaction | 250 | Legatum | DISC 250 | 1993 | 2005 | 0 | 9576184 | Retained | Failed
MyMI-prod | Eclipse_MI.FactSignedTransaction | 2987 | Legatum | DISC UK | 2001 | 2003 | 0 | 9680240 | Retained | Failed
MyMI-prod | Eclipse_MI.FactSignedTransaction | 2987 | Legatum | PL UK | 2008 | 9999 | 0 | 9782097 | Retained | Failed
MyMI-prod | Eclipse_MI.FactSignedTransaction | 2987 | Legatum | PL UK | 2014 | 9999 | 0 | 9880683 | Retained | Failed

## DimINW_Risk
Procedure O/p | DAL Server table Column Order
RISK_ID | RISK_ID
FULL_UW_REF | FULL_UW_REF
TOI_CODE | TOI_CODE
MAJOR_CLASS | MAJOR_CLASS
MINOR_CLASS | MINOR_CLASS
SUB_CLASS | SUB_CLASS
PERIOD_OF_POLICY_FROM_DATE | PERIOD_OF_POLICY_FROM_DATE
PERIOD_OF_POLICY_TO_DATE | PERIOD_OF_POLICY_TO_DATE
INSURED_NAME | INSURED_NAME
INSURER_NAME | INSURER_NAME
INSURER_ID | INSURER_ID
UNIQUE_MARKET_REF | UNIQUE_MARKET_REF
SIGNED_LINE_PCT | SIGNED_LINE_PCT
SIGNED_ORDER_PCT | SIGNED_ORDER_PCT
WRITTEN_LINE_PCT | WRITTEN_LINE_PCT
WRITTEN_ORDER_PCT | WRITTEN_ORDER_PCT
ESTIMATED_SIGNING_PCT | ESTIMATED_SIGNING_PCT
OCCURRING_OR_ATTACHING_CODE | OCCURRING_OR_ATTACHING_CODE
TERRITORIAL_SCOPE | TERRITORIAL_SCOPE
INSURED_TERRITORIAL_SCOPE | INSURED_TERRITORIAL_SCOPE
ACCOUNT_NUM | ACCOUNT_NUM
BKR_PSEUDONYM | BKR_PSEUDONYM
BKR_NAME | BKR_NAME
CONTRACT_TYPE_CODE | CONTRACT_TYPE_CODE
CONTRACT_TYPE_DESC
RISK_STATUS_CODE | RISK_STATUS_CODE
COVERHOLDER_NAME | COVERHOLDER_NAME
REINST_TERMS_DESC | REINST_TERMS_DESC
RISK_SECTION_CCY_LIMIT_CODE | RISK_SECTION_CCY_LIMIT_CODE
RISK_SECTION_CCY_LIMIT_AMT | RISK_SECTION_CCY_LIMIT_AMT
XL_EXCESS_AMT | XL_EXCESS_AMT
LIMIT_BASIS | LIMIT_BASIS
LEADER_STATUS | LEADER_STATUS
CONTRACT_TYPE_DESC
REPORTING_FLAG | REPORTING_FLAG
DAL
REPORTING_YEAR | REPORTING_QUARTER | PERIOD_TYPE | PERIOD_NUMBER | TRANSACTION_DATE | CLAIM_ID | LOSS_EVENT_ID | RISK_ID | CLASS_ID | UW_YEAR | SETT_CCY_CODE | ORIG_CCY_CODE | LLOYDS_RISK_CODE | TRUST_FUND_CODE | PAYMENT_TYPE | FIL_CODE_2 | FIL_CODE_4 | FIL_CODE | OS_TOTAL_MVT_SETT_CCY | OS_TOTAL_MVT_ORIG_CCY | REPORTING_FLAG | DATE_OF_LOAD
1993 | 4 | M | 10 | 1993-10-01 | 24347 | 6998 | 281633 | 1089 | 1993 | GBP | AUD | XE |  | Cash |  |  |  | 39894.5014 | 69580 | LEGATUM | 2022-08-18
1994 | 2 | M | 6 | 1994-06-01 | 24347 | 6998 | 281633 | 1089 | 1993 | GBP | AUD | XE |  | Cash |  |  |  | -39894.5014 | -69580 | LEGATUM | 2022-08-18

## Fact_INW_OSClaim_Analysis
DAL
REPORTING_YEAR | REPORTING_QUARTER | PERIOD_TYPE | PERIOD_NUMBER | TRANSACTION_DATE | CLAIM_ID | LOSS_EVENT_ID | RISK_ID | CLASS_ID | UW_YEAR | SETT_CCY_CODE | ORIG_CCY_CODE | LLOYDS_RISK_CODE | TRUST_FUND_CODE | PAYMENT_TYPE | FIL_CODE_2 | FIL_CODE_4 | FIL_CODE | OS_TOTAL_MVT_SETT_CCY | OS_TOTAL_MVT_ORIG_CCY | REPORTING_FLAG | DATE_OF_LOAD
1993 | 4 | M | 10 | 1993-10-01 | 24347 | 6998 | 281633 | 1089 | 1993 | GBP | AUD | XE |  | Cash |  |  |  | 39894.5014 | 69580 | LEGATUM | 2022-08-18
1994 | 2 | M | 6 | 1994-06-01 | 24347 | 6998 | 281633 | 1089 | 1993 | GBP | AUD | XE |  | Cash |  |  |  | -39894.5014 | -69580 | LEGATUM | 2022-08-18
MYMI
REPORTING_YEAR | REPORTING_QUARTER | PERIOD_TYPE | PERIOD_NUMBER | TRANSACTION_DATE | CLAIM_ID | LOSS_EVENT_ID | RISK_ID | CLASS_ID | UW_YEAR | SETT_CCY_CODE | ORIG_CCY_CODE | LLOYDS_RISK_CODE | TRUST_FUND_CODE | PAYMENT_TYPE | FIL_CODE_2 | FIL_CODE_4 | FIL_CODE | OS_TOTAL_MVT_SETT_CCY | OS_TOTAL_MVT_ORIG_CCY | REPORTING_FLAG
1993 | 4 | M | 10 | 1993-10-01 | 24347 | 6998 | 281633 | 1089 | 1993 | GBP | AUD | XE |  | Cash |  |  |  | 39894.5015 | 69580 | RITC Legatum
1994 | 2 | M | 6 | 1994-06-01 | 24347 | 6998 | 281633 | 1089 | 1993 | GBP | AUD | XE |  | Cash |  |  |  | -39894.5015 | -69580 | RITC Legatum
OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | NOT OK | OK
OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | OK | NOT OK | OK

## SIT Status-Task(MYMI-Test)
BRD Ref | Requirement Details from BRD | Task No. | Task Details | Test Status | Evidence - Screenshot/ DB Table | List of Tables/views | Comments
5.1 | Modify Riverstone View to provide AS-AT data | 98672 | SIT Testing - Inwards Robin DAL | Passed | Evidence available in Table under QA schema |  | Test includes extract data comparison between MYMI & DAL and Table/view mapping For Fact INW_OS_CLAIM, these measure have been excluded to validate due to rounding issues which causes failure ('OS_TOTAL_MVT_ORIG_CCY','OS_TOTAL_MVT_SETT_CCY') 30th Aug, 2022 - All the views are passed and the columns in view is same as base table except ROW_ID column which is not required for RS. Also, Contract_Type_DESC column is missing in INW_RISK & OUTW_RISH views although this column is available in the base table. I have been advised by Rishi that, this can be ignored
5.1 | Modify Riverstone View to provide AS-AT data | 98673 | SIT Testing - Outwards Legatum DAL | Passed
5.1 | Modify Riverstone View to provide AS-AT data | 98674 | SIT Testing - Robin Outwards DAL | Passed
5.2 | Remove Temporary Adjustments | 85590 | SIT Testing - Remove Temporary Adjustment From Outward Facts | To be Tested |  |  | 30th Aug, 2022 This cannot be tested in MYMI-Test To test this, New temp.adjustment data need to be key-ed in data in MYMI-Dev
5.3 | Remove Claim_ID from Outward Fact | 85765 | SIT Testing - Remove Claim_ID from Outward Fact | Completed/ Passed | Screenshot TE_Req5.3_Remove_Claim_ID_from_Outward Fact.PNG
5.4 | Modify Risk_ID of Outward Fact | 98685 | SIT Testing - Modify Risk ID in Outward Fact | Passed | No evidence required as the view mapping test passed and I can pass this test based on view mapping test |  | As I don't see any failure from the view mapping test, I am passing this test. I have sent a message to clarify the column name InwardRiskRef / Inwards_Reference? Which one is correct?
5.5 | Remove Outward Written Premium Fact | 98687 | SIT Testing - Remove Outward Written Premium Fact | Pending Testing/ Passed | OUTW_Written_Premium_Control OUTW_Written_Premium_Extract |  | Table/View still exists #100056 raised to address this #100056 is closed as this is not a bug and will be addressed at the end of the project once UAT is signed off ( as advised by Rishi) I don't think this need to be tested as the project team needs to take care of once UAT is signed off
5.6 | Distinguish between Robin and Legatum transaction in feed | 98688 | SIT Testing - Distinguish between Robin and Legatum transaction in feed - Acceptance Criteria 1 | Completed/ Passed | TE_Req5.5_Check_RS_View_For_Reporting_Flag.xls |  | All view got the column reporting_flag Legatum or Robin is available in view not in the base table
|  |  | SIT Testing - Distinguish between Robin and Legatum transaction in feed - Acceptance Criteria 2 | Passed | Screenshot - TE_Req5.6_Check_RS_View_For_Adjusted_&_Unknown_HardCodedValue_AC2 |  | Clarification about acceptance criteria 2 - to be discussed with Rish 31st Aug - Test Completed
5.8 | Frequency of Data feed | 98692 | SIT Testing - Frequency of Data Feed | Pending Testing/ Passed | This cannot be tested as the schedule is not visible to QA team. Dev team can confirm this |  | The frequency of the process is once in a week which is on Sunday. It ran successfully on Sun 21st Aug. I will monitor for next Sunday 28th and then I will pass this test 31th Aug 2022 - I think I will pass this test from SIT perspective. This will will be taken care by Dev/BaU team to schedule the process
5.9 | MYMI Indicator for Robin Inward and Outward Transaction | 86116 | SIT Testing - Inwards BNB flag for Robin & Legatum (Inward Only) | Completed/ Passed Fix Needed???? | [QA].[BNB_Switch_Config_Check] | DWH_MI Table List - 15 Eclipse_MI TableList - 16 | Totally 16 records Failed 8 records for DWH_MI tables + 8 records for Eclipse MI Table #99911 Bug has been raised to address these failures 30th Aug, 2022 - Prod data analsis done and bug has been updated with the details. My output being analysed by Rishi
5.9 | MYMI Indicator for Robin Inward and Outward Transaction | 89354 | SIT Testing - ORI Robin & Legatum Flag (Outward) | Completed/ Passed | Simply run the SQL script. There is no QA table for evidence | FactOriTransaction | DimGroupClassID NOT in (1101,1128, 343) -- Included as advised by Rishi on 18th Aug, 2022 I think this is due to IsDeleted Flag, But Rishi will further update SQL script to verify the result is FactOriTransaction_Using_GroupClass_For_Legatum_Records.SQL This script will display the failed records. This test is passed as long as the script returns 0 records
|  |  |  | To be Tested |  | FactOriContractCount | 16/08/2022 - Rishi said, there will be some config changes to be done and awaiting to be implmented in MYMI-Test 30th Aug, 2022 - According to Bau team Avinash, this will be implemented in Test sometimes this week commencing 30th Aug. So, Testing cannot be execute until this is implemented
5.1 | Exclude ORI Contract Ref from Outward Fact | 98422 | SIT Testing - Exclude ORI Contract Ref from Outward Fact | Completed / Passed | List of evidence - Table [QA].[TE_FCC_AC1a_Req510] [QA].[TE_FCC_AC1b_Req510] [QA].[TE_FCC_AC2_Req510] [QA].[TE_FCC_AC4_Req510] [QA].[TE_FOT_AC1a_Req510] [QA].[TE_FOT_AC1b_Req510] [QA].[TE_FOT_AC2_Req510] [QA].[TE_FOT_AC4_Req510] | FactOriTransaction FactOriContractCount

## SIT Status-Task(MYMI-Test) (2)
BRD Ref | Requirement Details from BRD | Task No. | User Story | Task Details | Test Status | Evidence - Screenshot/ DB Table | List of Tables/views | Comments
5.1 | Modify Riverstone View to provide AS-AT data | 98672 | 86740 | SIT Testing - Inwards Robin DAL | Passed | Evidence available in Table under QA schema |  | Test includes extract data comparison between MYMI & DAL and Table/view mapping For Fact INW_OS_CLAIM, these measure have been excluded to validate due to rounding issues which causes failure ('OS_TOTAL_MVT_ORIG_CCY','OS_TOTAL_MVT_SETT_CCY') 30th Aug, 2022 - All the views are passed and the columns in view is same as base table except ROW_ID column which is not required for RS. Also, Contract_Type_DESC column is missing in INW_RISK & OUTW_RISH views although this column is available in the base table. I have been advised by Rishi that, this can be ignored
5.1 | Modify Riverstone View to provide AS-AT data | 98673 | 86582 | SIT Testing - Outwards Legatum DAL | Passed
5.1 | Modify Riverstone View to provide AS-AT data | 98674 | 86747 | SIT Testing - Robin Outwards DAL | Passed
5.2 | Remove Temporary Adjustments | 85590 | 84072 | SIT Testing - Remove Temporary Adjustment From Outward Facts | To be Tested |  |  | 30th Aug, 2022 This cannot be tested in MYMI-Test To test this, New temp.adjustment data need to be key-ed in data in MYMI-Dev
5.3 | Remove Claim_ID from Outward Fact | 85765 | 84073 | SIT Testing - Remove Claim_ID from Outward Fact | Completed/ Passed | Screenshot TE_Req5.3_Remove_Claim_ID_from_Outward Fact.PNG
5.4 | Modify Risk_ID of Outward Fact | 98685 | 84075 | SIT Testing - Modify Risk ID in Outward Fact | Passed | No evidence required as the view mapping test passed and I can pass this test based on view mapping test |  | As I don't see any failure from the view mapping test, I am passing this test. I have sent a message to clarify the column name InwardRiskRef / Inwards_Reference? Which one is correct?
5.5 | Remove Outward Written Premium Fact | 98687 | 84074 | SIT Testing - Remove Outward Written Premium Fact | Pending Testing/ Passed | OUTW_Written_Premium_Control OUTW_Written_Premium_Extract |  | Table/View still exists #100056 raised to address this #100056 is closed as this is not a bug and will be addressed at the end of the project once UAT is signed off ( as advised by Rishi) I don't think this need to be tested as the project team needs to take care of once UAT is signed off
5.6 | Distinguish between Robin and Legatum transaction in feed | 98688 | 84089 | SIT Testing - Distinguish between Robin and Legatum transaction in feed - Acceptance Criteria 1 | Completed/ Passed | TE_Req5.5_Check_RS_View_For_Reporting_Flag.xls |  | All view got the column reporting_flag Legatum or Robin is available in view not in the base table
|  |  |  | SIT Testing - Distinguish between Robin and Legatum transaction in feed - Acceptance Criteria 2 | Passed | Screenshot - TE_Req5.6_Check_RS_View_For_Adjusted_&_Unknown_HardCodedValue_AC2 |  | Clarification about acceptance criteria 2 - to be discussed with Rish 31st Aug - Test Completed
5.8 | Frequency of Data feed | 98692 | 84092 | SIT Testing - Frequency of Data Feed | Pending Testing/ Passed | This cannot be tested as the schedule is not visible to QA team. Dev team can confirm this |  | The frequency of the process is once in a week which is on Sunday. It ran successfully on Sun 21st Aug. I will monitor for next Sunday 28th and then I will pass this test 31th Aug 2022 - I think I will pass this test from SIT perspective. This will will be taken care by Dev/BaU team to schedule the process
5.9 | MYMI Indicator for Robin Inward and Outward Transaction | 86116 | 84087 | SIT Testing - Inwards BNB flag for Robin & Legatum (Inward Only) | Completed/ Passed Fix Needed???? | [QA].[BNB_Switch_Config_Check] | DWH_MI Table List - 15 Eclipse_MI TableList - 16 | Totally 16 records Failed 8 records for DWH_MI tables + 8 records for Eclipse MI Table #99911 Bug has been raised to address these failures 30th Aug, 2022 - Prod data analsis done and bug has been updated with the details. My output being analysed by Rishi 7th Sep, 2022 An additional test is executed by using PolicyYOAId instead of DimYOAId and there are no failures from Latest Calendar and Financial Partition Using PolicyYOAID Evidence [QA].[BNB_Switch_Config_Check_PolicyYOA_PROD] [QA].[BNB_Switch_Config_Check_PolicyYOA_FinPartition_PROD] As confirmed by Roop that #99911 bug doesn't have any impact on data being sent to RS. Based on that, this task is closed now
5.9 | MYMI Indicator for Robin Inward and Outward Transaction | 89354 | 84088 | SIT Testing - ORI Robin & Legatum Flag (Outward) | Completed/ Passed | Simply run the SQL script. There is no QA table for evidence | FactOriTransaction | DimGroupClassID NOT in (1101,1128, 343) -- Included as advised by Rishi on 18th Aug, 2022 I think this is due to IsDeleted Flag, But Rishi will further update SQL script to verify the result is FactOriTransaction_Using_GroupClass_For_Legatum_Records.SQL This script will display the failed records. This test is passed as long as the script returns 0 records
[5 empty] | To be Tested |  | FactOriContractCount | 16/08/2022 - Rishi said, there will be some config changes to be done and awaiting to be implmented in MYMI-Test 30th Aug, 2022 - According to Bau team Avinash, this will be implemented in Test sometimes this week commencing 30th Aug. So, Testing cannot be execute until this is implemented 7th Sep, 2022 This change could be a big as Rishi is going to be in touch with Graham to discuss the impact
5.1 | Exclude ORI Contract Ref from Outward Fact | 98422 | 84097 | SIT Testing - Exclude ORI Contract Ref from Outward Fact | Completed / Passed | List of evidence - Table [QA].[TE_FCC_AC1a_Req510] [QA].[TE_FCC_AC1b_Req510] [QA].[TE_FCC_AC2_Req510] [QA].[TE_FCC_AC4_Req510] [QA].[TE_FOT_AC1a_Req510] [QA].[TE_FOT_AC1b_Req510] [QA].[TE_FOT_AC2_Req510] [QA].[TE_FOT_AC4_Req510] | FactOriTransaction FactOriContractCount

## Sheet2
User Story | User Story - Details | Task Ref | Req. Ref | Test Script (SQL Script File Name) | Tested in Env | Test Status | Comments / Evidence Details
86582 86740 86747 | Modify MYMI Extract Procedures to Include Legatum Tx - Outwards Modify MYMI Extract Procedures to Include Robin Tx - Inwards Modify MYMI Extract Procedures to Include Robin Tx - Outwards Tests include Data comparison between MYMI - DAL server (Tables) + DAL Server view mapping (between base table/view) | 98673 98672 98674 | 5.1 | Inward Data Comparison scripts MYMITest_Check_DataComparison_Control_INW_OSClaim_v0.1.SQL MYMITest_Check_DataComparison_Control_INW_PaidClaim_v0.1.SQL MYMITest_Check_DataComparison_Control_INW_Premium_v0.1.SQL MYMITest_Check_DataComparison_Control_INW_WrittenPremium_v0.1.SQL MYMITest_Check_DataComparison_DIM_INW_Group_Class_v0.4.SQL MYMITest_Check_DataComparison_DIM_INW_Loss_v0.2.SQL MYMITest_Check_DataComparison_DIM_INW_LossEvent_v0.2.SQL MYMITest_Check_DataComparison_DIM_INW_RISK_v0.2.SQL MYMITest_Check_DataComparison_FACT_INW_OSClaim_with_NOMeasurev0.4.SQL MYMITest_Check_DataComparison_FACT_INW_OSClaim_v0.3.SQL MYMITest_Check_DataComparison_FACT_INW_PaidClaim_v0.3.SQL MYMITest_Check_DataComparison_FACT_INW_Premium_v0.3.SQL MYMITest_Check_DataComparison_FACT_INW_WrittenPremium_v0.3.SQL Outward Data Comparison scripts MYMITest_Check_DataComparison_C_DIM_OUTW_Group_Class_v0.2.SQL MYMITest_Check_DataComparison_C_DIM_OUTW_LossEvent_v0.2.SQL MYMITest_Check_DataComparison_C_DIM_OUTW_RIContract_v0.2.SQL MYMITest_Check_DataComparison_C_DIM_OUTW_RIContractAcc_v0.2.SQL MYMITest_Check_DataComparison_C_DIM_OUTW_RIContractCcyLimit_v0.3.SQL MYMITest_Check_DataComparison_C_DIM_OUTW_RIContractIns_v0.2.SQL MYMITest_Check_DataComparison_C_DIM_OUTW_Risk_v0.2.SQL MYMITest_Check_DataComparison_C_FACT_OUTW_OSClaim_v0.2.SQL MYMITest_Check_DataComparison_C_FACT_OUTW_OSPremium_v0.2.SQL MYMITest_Check_DataComparison_C_FACT_OUTW_PaidClaim_v0.2.SQL MYMITest_Check_DataComparison_C_FACT_OUTW_PaidPremium_v0.2.SQL MYMITest_Check_DataComparison_Control_OUTW_OSClaim_v0.1.SQL MYMITest_Check_DataComparison_Control_OUTW_OSPremium_v0.1.SQL MYMITest_Check_DataComparison_Control_OUTW_PaidClaim_v0.1.SQL MYMITest_Check_DataComparison_Control_OUTW_PaidPremium_v0.1.SQL View mapping script Req5.1_ViewMapping_Test.SQL | MYMI-Test | Passed | Tasks Closed
84071 | Remove Temporary Adjustment from Inward Facts | 85587 | 5.2 | 84071_Check_Temp_Adj_Data_INW_Control_OSClaim_v0.1.SQL 84071_Check_Temp_Adj_Data_INW_Control_PaidClaim_v0.1.SQL 84071_Check_Temp_Adj_Data_INW_Control_Premium_v0.1.SQL 84071_Check_Temp_Adj_Data_INW_Control_WrittenPremium_v0.1.SQL 84071_Check_Temp_Adj_Data_INW_FACT_OSClaim_v0.1.SQL 84071_Check_Temp_Adj_Data_INW_FACT_PaidClaim_v0.1.SQL 84071_Check_Temp_Adj_Data_INW_FACT_Premium_v0.1.SQL 84071_Check_Temp_Adj_Data_INW_FACT_WrittenPremium_v0.1.SQL | MYMI-Dev | Passed | Based on the tests from MYMI-Dev, this task is closed
84072 | Remove Temporary Adjustment From Outward Facts | 85590 | 5.2 |  |  | Pending Test | SQL scripts still to be developed
84073 | Remove Claim_ID from Outward Fact | 85765 | 5.3 | Req5.3_Remove_Claim_ID_from_Outward Fact.SQL | MYMI-Test |  | Task Closed
84075 | Derive Inward Ref for Facultative Outward Contract | 98685 | 5.4 |  |  |  | No need to test. Task Closed
84074 | Remove Outward Loss Table | 98687 | 5.5 | Req5.5_Check_Remove_Outward_Written_Premium_Fact.SQL | MYMI-Test | Pending Test | Table/View still exists #100056 raised to address this #100056 is closed as this is not a bug and will be addressed at the end of the project once UAT is signed off ( as advised by Rishi) I don't think this need to be tested as the project team needs to take care of once UAT is signed off
84089 | Change Reporting Flag in Legatum Feed | 98688 | 5.6 | Req5.6_Check_RS_View_For_Reporting_Flag_AC1.SQL Req5.6_Check_RS_View_For_Adjusted_&_Unknown_HardCodedValue_AC2.SQL | MYMI-Test |  | Task Closed
84090 | Develop Reconciliation Process | N/A | 5.7 | No SQL script from QA |  |  | There is no SIT Task as the testing is applicable only for Dev team and n/a for QA
84092 | Inwards and Outwards Data Frequency Change | 98692 | 5.8 | It appears to be based on the data from MYMI-Test, the process is running on Wed & Sun. But Dev team can confirm this. If so, the schedule needs to be amended before go-live as per requirement to run once a week | MYMI-Test |  | 2nd Sept, 2022 - Assigned this task to Rishi to confirm the schedule from ADF
84087 | Robin Flag for Inward: BNB Switch Change | 86116 | 5.9 | BNB_Legatum_&_Robin_Config_Check_DWH_&_Eclipse_MI_Tables _30thAug2022.SQL Check_BNB_Result.SQL SQL Scripts using PolicyYOAID BNB_Legatum_&_Robin_Config_Check_Eclipse_MI_Tables _using_PolicyYOAID_MYMIProd_LatestPartition.SQL BNB_Legatum_&_Robin_Config_Check_Eclipse_MI_Tables _using_PolicyYOAID_MYMIProd_LatestFinlPartition_3_Tables.SQL | MYMI-Test |  | Awaiting outcome from Rishi's analysis about my Production output. #99911 bug is raised 7th Sep, 2022 An additional test is executed by using PolicyYOAId instead of DimYOAId and there are no failures from Latest Calendar and Financial Partition Using PolicyYOAID Evidence [QA].[BNB_Switch_Config_Check_PolicyYOA_PROD] [QA].[BNB_Switch_Config_Check_PolicyYOA_FinPartition_PROD] As confirmed by Roop that #99911 bug doesn't have any impact on data being sent to RS. Based on that, this task is closed now
84088 | Robin Flag for Outward Transaction. | 89354 | 5.9 | FactOriContractCount_Using_GroupClass.SQL | MYMI-Test |  | Awaiting for the config changes implementation in MYMI-Test 7th Sep, 2022 This change could be a big as Rishi is going to be in touch with Graham to discuss the impact
84097 | Exclude ORI Transaction from Legatum and Robin Outward Transaction | 98422 | 5.1 | AC1a_FACTOriTransaction_Legatum2018_Req5.10_v0.2.SQL AC1b_FACTOriTransaction_Legatum2018ADJ_Req5.10_v0.2.SQL AC2_FACTOriTransaction_Robin2021_&_Robin2021C_Req5.10_v0.2.SQL AC4_FACTOriTransaction_Excluded_ContractRef_as_Retained_Req5.10_v0.2.SQL AC1a_FACTOriContractCount_Legatum2018_Req5.10_v0.2.SQL AC1b_FACTOriContractCount_Legatum2018ADJ_Req5.10_v0.2.SQL AC2_FACTOriContractCount_Robin2021_&_Robin2021C__Req5.10_v0.2.SQL AC4_FACTOriContractCount_Excluded_ContractRef_as_Retained_Req5.10_v0.2.SQL | MYMI-Test |  | Tasks Closed